## Slide 1: VELUX STIFTUNG RETINOBLASTOMA MOLECULAR RESEARCH PROJECT: IMPLEMENTATION
Dr. Lucy Njambi
Dr. Helen Dimaras
15.05.2024

## Slide 2: Objectives
Components of the project
Roles of the team members
Timelines

## Slide 3: BUILDING CAPACITY IN MOLECULAR CANCER RESEARCH IN KENYA THROUGH ANALYSIS OF RETINOBLASTOMA HETEROGENEITY

## Slide 4
Ophthalmology
Genetic testing
Pathology
Sequencer
KAVI
CEBIB
Capacity building
SickKids
Training
Blood
Tumour
PhD
MSc
Skills transfer
Modules
Consumables
support
Biomedical Research

## Slide 5: Roles : Retinoblastoma Genetics Working Group
Clinicians
Ophthalmologist
Geneticist
Nurse/ counsellor
Samples
Clinical interpretation
Communication
Pathologists
Confirm
Diagnosis
Tissue handling
Protocols
Molecular scientist/
Bioinformatician
DNA isolation
Library preps
NGS
Genomic reads
& Interpretation
Training & Biomedical Research capacity building

## Slide 6: Project Timelines: September 2023 – August 2027
Deliverables Responsibility Support Timelines
Y1 Y2 Y3 Y4
Deliverables Responsibility Support Timelines
Y1 Y2 Y3 Y4

## Slide 7: Timelines: Where Are We? : Genetic Testing
Deliverables Responsibility Support Timelines
Q1 Q2 Q3 Q4

## Slide 8: Evaluation
What’s Working well
Project team in place
Approvals
Consumables & Biofreezer ordered
Protocols adaptation ongoing
Delay/ Challenge
Inflation
Delay in consumable procurement
Delay PhD registration
Specimen collection and lab work yet to begin

## Slide 9: Timelines: Where Are We? Capacity Building
Deliverables Responsibility Support Timelines
Q1 Q2 Q3 Q4

## Slide 10: Evaluation
What’s Working Well
Training workshop for project staff and stakeholders completed
Delay/ Challenge
Training modules curriculum and timing yet to be decided

## Slide 11: Timelines: Where Are We? Networking/ Collaborations
Deliverables Responsibility Support Timelines
Q1 Q2 Q3 Q4

## Slide 12: Evaluation
What's Working Well
Project Team and stakeholders meeting
Observer-ship planning on course
Partnership assessment tool to be proposed today
Delay/ Challenge
Budgetary constrains
Competing tasks and priorities